## DWP Action Plan
DEER WORK PROGRAMME ACTION PLAN 2024
Purpose: demonstrate progress with key projects - linked to DWG recommendations
Strategic Theme | # | Project | Action | Lead Agency & Workstream | Outcome | Deer Working Group recommendation number(s) being addressed. | Progress: December 2023
LEGISLATION | 1 | New Deer/ Natural Environment (Scotland) Act | Natural Environment Bill: Provide policy input to articulate new deer/ natural environment bill that meets DWG recommendations and delivers mechanism to meet SBS targets. | Scottish Govt/ NatureScot, FLS, Scottish Forestry (Legislation) | New primary legislation | 1, 3, 4-16, 19-21, 24-28, 30, 54, 57, 60-72, 78, 95, 97, 98; | Submission submitted to Minister. Public consulatation anticipated early in 2024.
|  |  | Use of Shotguns: Minimise extent of use of shotguns to kill deer to improve deer welfare. | Scottish Govt/ NatureScot (Legislation) | Only allow shotgun use as authorised by NatureScot. | 5 | NatureScot has submitted advice to Scottish Government to authorise shotgun use. To be included in consultation anticipated early in 2024.
|  |  | Change to seasons: De-regulate current system; remove requirement for authorisation to shoot out-of-season, by removing /changing season for male & female deer. | Scottish Govt/ Nature Scot (Legislation) | Changes to secondary legislation removing close season for males and changing dates of close season for female deer | 8 | Scottish Government due to consult on potential changes to female deer close seasons early in 2024. Close season for male red, sika, roe and fallow deer in Scoland now removed.
|  |  | Fit & Competent Register: Establish a publically available register of persons competent to shoot deer. | NatureScot (Legislation) | Register of persons competent to shoot deer. | 13, 14, 15 | NatureScot has submitted advice to Scottsih Government on establishment of a 'fit and competent' register. To be included in consultation anticipated early in 2024.
DATA & RESEARCH. | 2 | Civtech - Satellite, Fixed Wing Aerial and UAV with AI | Develop new and innovative ways of counting deer to support move away from reliance on helicopter counts in the upland red deer range. | NatureScot, FLS (Operational Delivery) | Trail new technology and reduced use of helicopters but maintain functionality (accuracy of info, scale of count etc). | 87 | Trials of alternative techniques ongoing. Work with FLS on use of UAVs with high resolution cameras inc. thermal imaging. Trial to assess population assessment in woodland underway. WDBP Guide on use of drones for deer counting in prep. and aiming for publication early in spring 2024. Review of NatutreScot deer count policy and approach being undertaken.
| 3 | Deer On-line Services | Redevelopment of Deerline database: for issuing authorisations, assigning 'fit and competent' status and an online National Cull Database that meets UK Government data standards and accessibility. | NatureScot (Operational Delivery) | Re-developed Deerline database. | 55, 58, 59 | Deer On-line Services build ongoing. Aiming for completion by March 2024.
| 4 | Cull Plan Approval | Research, develop and implement a planned cull approval system for Scotland. | NatureScot (Operational Delivery) | Develop and pilot a cull approval system within the Operational Delivery Workstream priority areas | 93, 97 | NatureScot scoping data requirements, cost-benefit analysis, assessment of feasibility and options appraisal of a planned cull approval system. Operational Delivery Workstream priority areas identified and Action Plans being drafted.
| 5 | Linking deer densities, impacts and cull planning | Improve understanding of the relationships between densities and impacts and how this relates to delivery of public interest outcomes and investment; summarise and assess existing research with a view to better articulating likely habitat responses to different deer densities. | NatureScot (Operational Delivery) | Shift in emphasis towards measuring impacts as opposed to a reliance on counting. Published guidance on densities and impacts - which informs Regulation and Incentives workstreams | 86, 87 | Have reviewed policies and procedures relating to deer densities, impacts and cull planning. Focus is now on deer data project and priorities are reviewing data collection, HIA methodologies and count methodologies.
| 6 | Deer Vehicle Collisions | Identify priority hotspots areas for DVCs and implement actions to mitigate | Transport Scotland, NatureScot (Operational Delivery) | Risk-based approach to identifying priority areas - ODW to consider to prioritise | 35-37 | Higher risk areas, based on data to 2021, identified and work around mitigation measures underway including review of mitigation measures and their efficacy and some targetted implementation of measures at a local level.
|  |  | Develop a cloud-based portal to store and make publically available all national DVC records |  | Publically accessible, real-time DVC database |  | Records available via appropriate GIS link, on request.
CODES OF PRACTCE AND BEST PRACTICE. | 7 | Wild Deer Best Practice | Revise WDBP content to incorporate changes resulting from DWG Recs. and delivery of wider Deer Work Programme through Strategic Deer Board and Workstreams | NatureScot (Operational Delivery) | NatureScot has committed to supporting the WDBP Project for five years and guidance and training events meet new requirements and demands in line with DWG recommendations and new deer legislation. | 11, 29, 30, 47-50, 80 | New guide for night vision and thermal imaging published and practical event held. Programme of BP events for 2024 being planned. New guide on drone use for counting in prep. for publication in February. Guide on rifles and ammunition updated and published. Non-lead ammunition info. sheet in prep. Review of all guides started and potential new guides being identified. Website receiving 'facelift' for 2024. Steering Group workshops on Deer Working Group recommendations completed.
| 8 | Deer Code | Revise Deer Code and other deer related guidance. Dependent on update to WDBP following new legislation | NatureScot (Operational Delivery) | Revised Deer Code & other guidance | 79, | NatureScot will engage with relevant stakeholders to revise Code of Practice once new legislation in place.
POLICY | 9 | Policy Development & Implementation | Strategic Deer Board maintain oversight of development & delivery of Deer Work Programme and Action Plan through SBS 2030 - 45 | Scottish Govt, NatureScot, FLS, Scottish Forestry, National Parks (Strategic Deer Board) | Deer Work Programme agreed. Delivery of SBS outcomes 2030 & 2045 | 17, 40, 41, 53, 75, 77, 81, 82, 84, 88-90, 99 | Board and workstreams established and delivering a programme of work. Deer Action Plan drafted and being updated quarterly.
| 10 | ODW Priority Areas | Regulation, Incentives & Operational Delivery workstreams to develop and implement a programme of work to direct delivery on the ground in priority locations and more effective use of NatureScot regulatory powers | Scottish Govt, NatureScot, FLS, Scottish Forestry, National Parks (Strategic Deer Board & all workstreams) | Rationale and Programme of work agreed and priority locations for action on-the-ground agreed | 31, 33, 34, 36, 37, 51, 52, 76, 85, 96 | Operational Delivery Workstream has developed criteria and maps to prioritise operational activity on the ground. Action Plans for delivery drafted. Key locations for use of Regulation identified and being progressed.
| 11 | Lowland Deer | Continue to work with LAs on landscape approaches, particularly green space and woodland creation, through continued funding and support for Deer Statements at LA scale (ongoing) | Scottish Forestry, FLS, NatureScot (Operational Delivery) | Action Plans for priority areas will include lowland deer | 51, 52, 91 | Operational Delivery Workstream has identified priority areas (including public land) where greater collaboration will be required. NatureScot is continuing to work with Local Authorities on landscape approaches through continued funding and support for Deer Statements (ongoing). Work progressing on population modelling and working with LDNS on venison incentives and capacity building.
| 12 | INNS | Control spread of non-native species. | NatureScot (Operational Delivery) | Action plan for regional delivery (taking a risk based approach) has been produced | 38, 39, 42-46 | Project scope to be defined; cross-reference with Scottish Plan for INNS surveillance, prevention and control to be completed.
SIGNIFICANT INCREASE IN NUMBER OF DEER HARVESTED PER ANNUM | 13 | Capacity Building | Work with the deer sector & colleges to identify future skills needs and build capacity and resilience | NatureScot (Operational Delivery, Incentives)) | Scope and review current capacity and future need | 80, 99 | Scoping report published. Further work being developed with the sector to look at barriers and constraints to future requirements. Best Practice - new guides published and being developed. BP events held and further events being planned. See also project 7 above.
| 14 | Infrastructure | Work with the deer sector to align larder infrastructure and capacity with future need. | FLS, NatureScot (Operational Delivery) | Scope current capacity and assessment of future need | 99 | Deer larder inventory with indication of capacity/location/throughput in development.
| 15 | Venison | Support the venison sector to build greater capacity and resilience to meet projected future demand from increased culls (including the testing of incentives). | Scottish Government - Scottish Food & Drink, NatureScot, Food Standards Scotland, FLS (Operational Delivery) | Scope and review of capacity to meet future need | 19-21, 23 | Working closely with Scottish Venison and Scottish Government. Pilot project re. venison subsidy established in Cairngorms National Park. Community stalking model at Creag Meagaidh NNR being developed elsewhere.
| 16 | Population baseline and trends and modelling including mapping scale, scope & extent of cull | a) Develop a better understanding of populations and denisties across all four deer species at a regional level for all of Scotland. i) Analysis of upland DMG red deer populations to identify the number of deer (10 deer per sq. km 'target'). ii) Develop and promote Sika deer policy. iii) Improve understanding of roe deer densities in woodland. iv) Improve understanding of extent of fallow deer. | NatureScot, FLS (Operational Delivery) | Verified population model for all species across all of Scotland and map the scale of harvest required to meet SBS 2030 & 2045 targets. | 2, 42-44, 87 | Population trends and modelling project underway. Will lead to better understanding of populations, densities and distributions.
|  |  | b) Gather more accurate information on number of deer harvested. | NatureScot | More accurate figures for number of deer across all species shot. | 55-59, 93, 96 | Deer Management System - app. in development.
|  |  | c) Work with RPID to increase coverage of cull returns. | NatureScot, Scottish Government | Increased geographical coverage off cull returns. | 58 | Working with RPID re. data sharing.