DEER WORK PROGRAMME ACTION PLAN, 2025/2026.

Progress with key projects linked to the Deer Working Group recommendations.

Strategic theme 1: Legislation.

Table 1a

Project: New Natural Environment (Scotland) Act.

| Action | Lead | Outcome | Associated Deer Working Group recommendation number(s). | Update for March 2026. |
| --- | --- | --- | --- | --- |
| Natural Environment Bill: Provide policy input to articulate new deer/ natural environment bill that meets Deer Working Group recommendations and delivers mechanism to meet Scottish Biodiversity Strategy targets. | Scottish Government/ NatureScot, Forestry and Land Scotland, Scottish Forestry. | New primary legislation | 1, 3, 4-16, 19-21, 24-28, 30, 54, 57, 60-72, 78, 95, 97, 98 | The Natural Environment Bill has been passed and is awaiting Royal Ascent. Thereafter, different elements come into force at different times, but no elements are expected to come into force for at least two months. |
| Use of Shotguns: Minimise extent of use of shotguns to kill deer to improve deer welfare. | Scottish Government/ NatureScot. | Only allow shotgun use as authorised by NatureScot. | 5 | The Natural Environment Bill has been passed and is awaiting Royal Ascent. Thereafter, different elements come into force at different times, but no elements are expected to come into force for at least two months. |
| Change to seasons: De-regulate current system; remove requirement for authorisation to shoot out-of-season, by removing /changing season for male and female deer. | Scottish Government/ NatureScot. | Changes to secondary legislation removing close season for males and changing dates of close season for female deer | 8 | The Natural Environment Bill has been passed and is awaiting Royal Ascent. Thereafter, different elements come into force at different times, but no elements are expected to come into force for at least two months. |
| Fit and Competent Register: Establish a publicly available register of persons competent to shoot deer. | NatureScot. | Register of persons competent to shoot deer. | 13, 14, 15 | The Natural Environment Bill has been passed and is awaiting Royal Ascent. Thereafter, different elements come into force at different times, but no elements are expected to come into force for at least two months. |

Strategic theme 2: Data and Research.

Table 2a.

Project: Deer counting technology and options.

| Action | Lead Agency | Outcome | Deer Working Group recommendation number. | Update for March 2026. |
| --- | --- | --- | --- | --- |
| Develop new and innovative ways of counting deer to support move away from reliance on helicopter counts in the upland red deer range. | NatureScot, Forestry and Land Scotland. | Trail new technology and reduced use of helicopters but maintain functionality e.g. accuracy and scale of count. | 87 | Trials of alternative techniques ongoing. Increased use of thermal drone imagery for woodland deer census work utilising external contract resource. NatureScot staff undertaking additional survey work. A review of census methodologies exploring the pros/cons of different techniques is underway. This is considering helicopter, satellite, fixed wing, drone, foot, fixed point/trail cam. photography and dung analysis work. Wild Deer Best Practice Guide on use of drones for deer counting due for publication. Review of NatureScot deer count policy and approach underway. |

Table 2b.

Project: Deer On-line Services

| Action | Lead Agency | Outcome | Deer Working Group recommendation number. | Update for March 2026. |
| --- | --- | --- | --- | --- |
| Redevelopment of Deerline database: for issuing authorisations, assigning 'fit and competent' status and creation of an online National Cull Database that meets UK Government data standards and accessibility. | NatureScot. | Re-developed Deerline database. | 55, 58, 59 | Deer On-line Services now live. |

Table 2c.

Project: Cull Plan Approval

| Action | Lead Agency | Outcome | Deer Working Group recommendation number. | Update for March 2026. |
| --- | --- | --- | --- | --- |
| Research, develop and implement a planned cull approval system for Scotland. | NatureScot. | Develop and pilot a cull approval system within the Operational Delivery Workstream priority areas. | 93, 97 | NatureScot reflecting on new powers under Natural Environment Bill in relation to culls and cull planning and looking at gathering more cull data to help inform cull planning. |

Table 2d.

Project: Linking deer densities, impacts and cull planning

| Action | Lead Agency | Outcome | Deer Working Group recommendation number. | Update for March 2026. |
| --- | --- | --- | --- | --- |
| Improve understanding of the relationships between deer densities and their impacts and how this relates to delivery of public interest outcomes and investment; summarise and assess existing research with a view to better articulating likely habitat responses to different deer densities. | NatureScot. | Shift in emphasis towards measuring impacts as opposed to a reliance on counting. Published guidance on densities and impacts - which informs Regulation and Incentives workstream. | 86, 87 | Policies and procedures relating to deer densities, impacts and cull planning reviewed. Deer data project to review data collection, review of Habitat Impact Assessment methodologies and census methodologies initiated. |

Table 2e.

Project: Deer Vehicle Collision (DVC) Project

| Action | Lead Agency | Outcome | Deer Working Group recommendation number. | Update for March 2026. |
| --- | --- | --- | --- | --- |
| Identify priority hotspots areas for Deer Vehicle Collisions and implement actions to mitigate them. | Transport Scotland, NatureScot. | Risk-based approach to identifying priority areas. | 35-37 | Autumn Deer Aware campaign completed. Vehicle speed data being analysed. Spring campaign to be developed. DVC project 2022-2024 completed and report published. New contract for 2025-2028 tendered. Project looking in detail at possible mitigation options on Isle of Lewis underway; due to report Q4. |
| Develop cloud-based portal to store and make publicly available all national Deer Vehicle Collision records. | Transport Scotland, NatureScot. | Publicly accessible DVC database | 35-37 | Options for making latest data available via Open Data Hub to be explored in new DVC project contract. |

Strategic theme 3: Codes of Practice and Best Practice.

Table 3a.

Project: Wild Deer Best Practice.

| Action | Lead Agency | Outcome | Deer Working Group recommendation number. | Update for March 2026. |
| --- | --- | --- | --- | --- |
| Revise Wild Deer Best Practice content to incorporate changes resulting from Deer working Group recommendations, and delivery of wider Deer Work Programme through Strategic Deer Board and Workstreams. | NatureScot. | NatureScot has committed to supporting the Wild Deer Best Practice Project for five years and guidance and training events meet new requirements and demands in line with Deer working Group recommendations and new deer legislation. | 11, 29, 30, 47-50, 80 | Review of Best Practice guides completed. Revised guides available on new Best Practice website. Potential new guides being identified. Review of Statutory Guidance completed. Practioner events for 2026 in development. |

Table 3b.

Project: Deer Code.

| Action | Lead Agency | Outcome | Deer Working Group recommendation number. | Update for March 2026. |
| --- | --- | --- | --- | --- |
| Revise Deer Code and other deer related guidance. Dependent on update to Wild Deer Best Practice guides following new legislation. | NatureScot. | Revised Deer Code and other guidance. | 79 | NatureScot is engaging with stakeholders regarding the revising of the Code of Practice and a steering group has been established. |

Strategic theme 4: Policy.

Table 4a.

Project: Policy Development & Implementation

| Action | Lead Agency | Outcome | Deer Working Group recommendation number. | Update for March 2026. |
| --- | --- | --- | --- | --- |
| Strategic Deer Board maintain oversight of development & delivery of Deer Work Programme and Action Plan through Scottish Biodiversity Strategy 2030 – 2045. | Scottish Government, NatureScot, Forestry and Land Scotland, Scottish Forestry, National Parks. | Deer Work Programme agreed. Delivery of Scottish Biodiversity Strategy outcomes 2030 & 2045. | 17, 40, 41, 53, 75, 77, 81, 82, 84, 88-90, 99 | Board established and delivering a programme of work. The number and remit of the workstreams being revised. National deer and venison management plan to be developed. Deer Action Plan drafted and updated every few months. |

Table 4b.

Project: Operational Delivery Workstream Priority Areas

| Action | Lead Agency | Outcome | Deer Working Group recommendation number. | Update for March 2026. |
| --- | --- | --- | --- | --- |
| Regulation, Incentives & Operational Delivery workstreams to develop and implement a programme of work to direct delivery on the ground in priority locations and more effective use of NatureScot regulatory powers. | Scottish Government, NatureScot, Forestry and Land Scotland, Scottish Forestry, National Parks. | Rationale and Programme of work agreed and priority locations for action on-the-ground agreed. | 31, 33, 34, 36, 37, 51, 52, 76, 85, 96 | Landscape-scale priority areas collectively identified by NatureScot, Scottish Water, Scottish Forestry, Forest and Land Scotland and Scottish Environmental Protection Agency. Operational Delivery Workstream has developed criteria and maps to prioritise operational deer-related activity on the ground. Action Plans for delivery drafted. |

Table 4c.

Project: Lowland Deer

| Action | Lead Agency | Outcome | Deer Working Group recommendation number. | Update for March 2026. |
| --- | --- | --- | --- | --- |
| Support Lowland Deer Network Scotland, develop an incentive scheme and continue to work with Local Authorities on landscape approaches, particularly green space and woodland creation, through continued funding and support for Deer Statements at Local Authority scale (ongoing). | Scottish Forestry, Forestry and Land Scotland, NatureScot. | Action Plans for priority areas will include lowland deer. | 51, 52, 91 | Operational Delivery Workstream has identified the Clyde Climate Forest as a priority area to focus on challenges around lowland deer management. NatureScot is continuing to work with Local Authorities on landscape approaches through continued funding and support for Deer Statements (ongoing). NatureScot, Forestry and Land Scotland, Transport Scotland and Scottish Forestry are increasing investment in Lowland Deer Network Scotland to support lowland deer management. Deer Management Incentive Scheme pilot (focussing on roe deer in the Central Belt) continued for 2025/ 2026. |

Table 4d.

Project: INNS

| Action | Lead Agency | Outcome | Deer Working Group recommendation number. | Update for March 2026. |
| --- | --- | --- | --- | --- |
| Control spread of non-native species. | NatureScot. | Action plan for regional delivery (taking a risk-based approach) has been produced. | 38, 39, 42-46 | Project scope to be defined; cross-reference with Scottish Plan for Invasive Non-Native Species surveillance, prevention and control to be completed. New sika policy drafted. Associated action plan being developed. Incentive scheme for sika management in place for 2025/206. |

Strategic theme 5: Significant increase in the number of deer harvested per annum.

Table 5a.

Project: Capacity Building

| Action | Lead Agency | Outcome | Deer Working Group recommendation number. | Update for March 2026. |
| --- | --- | --- | --- | --- |
| Work with the deer sector & colleges to identify future skills needs and build capacity and resilience. | NatureScot. | Capacity and assessment of future need scoped. | 80, 99 | Scoping report published. Further work being developed with the sector to look at barriers and constraints to future requirements. NatureScot attending Game & Wildlife Sector Skills Group. Engaging with groups of young stalkers looking particularly at the future of deer management and how to support them. Best Practice - review of guides completed, and new guides being developed. Website renewed and now live. Best Practice events for 2026 in development. |

Table 5b.

Project: Infrastructure

| Action | Lead Agency | Outcome | Deer Working Group recommendation number. | Update for March 2026. |
| --- | --- | --- | --- | --- |
| Work with the deer sector to align larder infrastructure and capacity with future need. | Forestry and Land Scotland, NatureScot. | Capacity and assessment of future need scoped. | 99 | Partnership project with SAOS working with stakeholders, including Lowland Deer Network Scotland and Scottish Venison, exploring community larder and processing infrastructure at various scales. Second round of funding applications now closed and successful applicants notified of funding support. |

Table 5c.

Project: Incentives

| Action | Lead Agency | Outcome | Deer Working Group recommendation number. | Update for March 2026. |
| --- | --- | --- | --- | --- |
| Develop incentive pilot schemes for culling focussing on a 'lowland' area for roe deer, a more northerly area for sika and the Cairngorms National Park Authority for red deer. | NatureScot, Cairngorms National Park Authority. | Increased culling of roe deer, red deer and sika in the respective target areas. | N/A | Deer Management Incentive Scheme pilots for 2025/2026 due to close March 2026. Additional schemes in the National Parks established. |

Table 5d.

Project: Venison

| Action | Lead Agency | Outcome | Deer Working Group recommendation number. | Update for March 2026. |
| --- | --- | --- | --- | --- |
| Support the venison sector to build greater capacity and resilience to meet projected future demand from increased culls (including the testing of incentives). | Scottish Government - Scottish Food & Drink, NatureScot, Food Standards Scotland, Forestry and Land Scotland. | Scope and review of capacity to meet future need. | 19-21, 23 | Working closely with Scottish Venison, SAOS, Lowland Deer Network Scotland, Scottish Government and other relevant parties to encourage and develop greater collaboration regarding use of deer larders. As part of Low Ground Venison Supply Chain Project, awarding grants to support development of new chiller facilities and larder improvements. Strategic Deer Board promoting community stalking on public land. Community stalking established at Creag Meagaidh National Nature reserve (NNR) and at Beinn Eighe NNR. |

Table 5e.

Project: Population baseline and trends and modelling including mapping scale, scope

and extent of cull

| Action | Lead Agency | Outcome | Deer Working Group recommendation number. | Update for March 2026. |
| --- | --- | --- | --- | --- |
| a) Develop a better understanding of populations and densities across all four deer species at a regional level for all of Scotland. i) Analysis of upland Deer Management Group red deer populations to identify the number of deer (10 deer per sq. km maximum). ii) Develop and promote sika policy. iii) Improve understanding of woodland deer densities. | NatureScot, Forestry and Land Scotland. | Verified population model for all species across Scotland and the scale of harvest required to meet Scottish Biodiversity Strategy 2030 & 2045 targets mapped. | 2, 42 - 44, 87 | Population trends and modelling completed and rolled out. Will lead to better understanding of populations, densities and distributions. i) Information from latest red deer counts being collated. ii) Action plan to accompany Sika policy being developed. iii) Camera trapping project initiated with methodology design and protocol being prepared. |
| b) Gather more accurate information on number of deer harvested. | NatureScot. | More accurate figures for number of deer across all species shot. | 55-59, 93, 96 | Deer App. tested in the pilot incentive schemes, on NNRs and on some private landholdings. Deer Online Services now available for on-line cull returns. |
| c) Work with RPID to increase coverage of cull returns. | NatureScot, Scottish Government. | Increased geographical coverage off cull returns. | 58 | Liaising with Scottish Government re. access to landholder information and project to increase coverage of cull returns underway. |